## PTW_Records
ptw_id | requester | requester_designation | area | permit_type | work_type(start/stop) | hazards_identified | controls | authoriser | authoriser_designation | issue_time | expiry_time | close_time | attachments | permit_status | missing_controls_flag | auto_generated_checklist | notes | issue_date | expiry_dt | is_past_expiry
PTW-5000 | Rahul Deshmukh | Shift Supervisor | Underground Tank Area | Excavation | start | Collapse/soil instability; Water ingress | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-09-11 08:45 | 2025-09-11 12:45 | 2025-09-11 10:45 | photo_area_22.jpg | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-09-11 | 2025-09-11 12:45 | FALSE
PTW-5001 | Shyamrao Jagtap | Rigger | Paint - Oven Area | Hot Work | start | Fire ignition; Combustible dust presence | Fire watch assigned; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-08-12 14:45 | 2025-08-12 22:45 | 2025-08-12 23:45 | isolation_certificate_12.pdf | Closed | Yes | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-08-12 | 2025-08-12 22:45 | FALSE
PTW-5002 | Shyamrao Jagtap | Rigger | Battery Area | Hot Work | start | Fire ignition | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-13 10:15 | 2025-10-13 22:15 | 2025-10-14 00:15 | lockout_tags.xlsx | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-10-13 | 2025-10-13 22:15 | FALSE
PTW-5003 | Sunita Gaikwad | Operator | Body Shop - Booth A | Confined Space | start | Engulfment risk | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-09-29 15:45 | 2025-09-29 23:45 | 2025-09-29 20:45 | isolation_certificate_12.pdf | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-29 | 2025-09-29 23:45 | FALSE
PTW-5004 | Ajay Kadam | Contractor Foreman | Maintenance Workshop | Electrical | stop | Live conductors | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-08-16 14:45 | 2025-08-17 14:45 | 2025-08-17 17:45 | lockout_tags.xlsx | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-16 | 2025-08-17 14:45 | FALSE
PTW-5005 | Mahesh Londhe | Loader Operator | Welding - Line 3 | Working at Height | stop | Fall from height; Wind gusts | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-09-13 11:45 | 2025-09-13 19:45 | 2025-09-13 22:45 | sds_hydrochloric.pdf | Closed | No | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-09-13 | 2025-09-13 19:45 | FALSE
PTW-5006 | Mahesh Londhe | Loader Operator | Body Shop - Booth A | Hot Work | start | Fire ignition; Combustible dust presence | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | HR Manager - Ms. Jyoti Rane | HR Manager | 2025-09-06 12:30 | 2025-09-06 18:30 | 2025-09-06 19:30 | scaffold_report_7.pdf | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-09-06 | 2025-09-06 18:30 | FALSE
PTW-5007 | Sanjay Mahajan | Fabrication Lead | Body Shop - Booth A | LOTO | stop | Pneumatic lines; Stored energy in springs | Energy isolation verified; Lock and tag present; Authorized personnel only; LOTO checklist completed | QA Head - Mr. Manoj Desai | QA Head | 2025-10-03 07:15 | 2025-10-03 19:15 | 2025-10-03 12:15 | isolation_certificate_12.pdf | Closed | No | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-10-03 | 2025-10-03 19:15 | FALSE
PTW-5008 | Anita Bhosale | Quality Inspector | Maintenance Workshop | Excavation | start | Water ingress; Collapse/soil instability | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned | Plant Manager - Mr. Amit Mehta | Plant Manager | 2025-08-23 08:15 | 2025-08-23 16:15 | 2025-08-23 14:15 | gas_test_45.pdf | Closed | Yes | Underground utility check; Shoring in place; Access ladder |  | 2025-08-23 | 2025-08-23 16:15 | FALSE
PTW-5009 | Rutuja Kale | Chemical Operator | Testing - Dyno Bay | LOTO | stop | Unexpected energization; Stored energy in springs | Energy isolation verified; Lock and tag present; Authorized personnel only; LOTO checklist completed | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-10-28 14:00 | 2025-10-28 18:00 | 2025-10-28 18:00 | sds_hydrochloric.pdf | Closed | No | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-10-28 | 2025-10-28 18:00 | FALSE
PTW-5010 | Rahul Deshmukh | Shift Supervisor | Stamping - Bay 1 | Working at Height | start | Unstable platform | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-08-21 07:30 | 2025-08-21 11:30 | 2025-08-21 17:30 | scaffold_report_7.pdf | Closed | No | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-08-21 | 2025-08-21 11:30 | FALSE
PTW-5011 | Mohan Dighe | External Contractor | Maintenance Workshop | Confined Space | start | Poor ventilation | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | HR Manager - Ms. Jyoti Rane | HR Manager | 2025-08-20 16:30 | 2025-08-21 04:30 | 2025-08-21 02:30 | isolation_certificate_12.pdf | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-08-20 | 2025-08-21 04:30 | FALSE
PTW-5012 | Deepak Raut | Maintenance Fitter | Body Shop - Booth A | Excavation | start | Water ingress | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-08-19 07:30 | 2025-08-19 11:30 | 2025-08-19 12:30 | isolation_certificate_12.pdf | Closed | Yes | Underground utility check; Shoring in place; Access ladder |  | 2025-08-19 | 2025-08-19 11:30 | FALSE
PTW-5013 | Nilesh Chavan | HVAC Technician | Underground Tank Area | Electrical | stop | Arc flash potential | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-29 10:30 | 2025-10-29 22:30 | 2025-10-29 18:30 | photo_area_22.jpg | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-10-29 | 2025-10-29 22:30 | FALSE
PTW-5014 | Suresh Patil | Technician | Assembly - Line 5 | Excavation | stop | Underground cable strike; Water ingress | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Plant Manager - Mr. Amit Mehta | Plant Manager | 2025-10-06 13:30 | 2025-10-06 21:30 | 2025-10-07 01:30 | lockout_tags.xlsx | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-10-06 | 2025-10-06 21:30 | FALSE
PTW-5015 | Anita Bhosale | Quality Inspector | Paint - Oven Area | Hot Work | stop | Combustible dust presence | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-09-16 07:15 | 2025-09-17 07:15 | 2025-09-16 23:15 | lockout_tags.xlsx | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-09-16 | 2025-09-17 07:15 | FALSE
PTW-5016 | Priya Joshi | Process Engineer | Body Shop - Booth A | LOTO | stop | Unexpected energization; Hydraulic pressure | Energy isolation verified; Lock and tag present; Authorized personnel only; LOTO checklist completed | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-10-22 07:00 | 2025-10-22 19:00 | 2025-10-22 10:00 | gas_test_45.pdf | Closed | No | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-10-22 | 2025-10-22 19:00 | FALSE
PTW-5017 | Shyamrao Jagtap | Rigger | Body Shop - Booth A | Electrical | stop | Arc flash potential; Damaged insulation | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-08-22 08:00 | 2025-08-22 12:00 |  | isolation_certificate_12.pdf | Open | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-22 | 2025-08-22 12:00 | TRUE
PTW-5018 | Priya Joshi | Process Engineer | Stamping - Bay 1 | Chemical Transfer | stop | Spill/runoff to drain | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-07 08:45 | 2025-10-08 08:45 | 2025-10-08 02:45 | scaffold_report_7.pdf | Closed | No | SDS reviewed; Spill kit available; Proper PPE |  | 2025-10-07 | 2025-10-08 08:45 | FALSE
PTW-5019 | Shyamrao Jagtap | Rigger | Underground Tank Area | LOTO | start | Unexpected energization | Energy isolation verified; Lock and tag present; Authorized personnel only; LOTO checklist completed | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-08-18 06:30 | 2025-08-18 12:30 | 2025-08-18 09:30 | gas_test_45.pdf | Closed | No | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-08-18 | 2025-08-18 12:30 | FALSE
PTW-5020 | Rahul Deshmukh | Shift Supervisor | Underground Tank Area | Working at Height | stop | Fall from height | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | HR Manager - Ms. Jyoti Rane | HR Manager | 2025-08-19 13:00 | 2025-08-19 21:00 |  | isolation_certificate_12.pdf | Open | Yes | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-08-19 | 2025-08-19 21:00 | TRUE
PTW-5021 | Asha Kulkarni | Maintenance Technician | Battery Area | Chemical Transfer | start | Ignition source nearby; Spill/runoff to drain | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-10-04 13:00 | 2025-10-05 01:00 | 2025-10-04 21:00 | none | Closed | No | SDS reviewed; Spill kit available; Proper PPE |  | 2025-10-04 | 2025-10-05 01:00 | FALSE
PTW-5022 | Mahesh Londhe | Loader Operator | Testing - Dyno Bay | Chemical Transfer | start | Ignition source nearby; Vapour inhalation | SDS reviewed; Proper PPE; Bonding & grounding; Secondary containment | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-09-03 14:15 | 2025-09-04 02:15 |  | hotwork_checklist_5.pdf | Open | Yes | SDS reviewed; Spill kit available; Proper PPE |  | 2025-09-03 | 2025-09-04 02:15 | TRUE
PTW-5023 | Deepak Raut | Maintenance Fitter | Maintenance Workshop | Electrical | start | Water ingress risk | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-08-16 08:30 | 2025-08-16 14:30 | 2025-08-16 12:30 | gas_test_45.pdf | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-16 | 2025-08-16 14:30 | FALSE
PTW-5024 | Pooja Nimbalkar | Safety Coordinator | Battery Area | Confined Space | stop | Engulfment risk | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-30 12:45 | 2025-10-31 00:45 | 2025-10-30 13:45 | scaffold_report_7.pdf | Closed | Yes | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-10-30 | 2025-10-31 00:45 | FALSE
PTW-5025 | Asha Kulkarni | Maintenance Technician | Paint - Oven Area | Working at Height | start | Unstable platform | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-09-12 14:30 | 2025-09-12 20:30 | 2025-09-12 17:30 | scaffold_report_7.pdf | Closed | No | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-09-12 | 2025-09-12 20:30 | FALSE
PTW-5026 | Rutuja Kale | Chemical Operator | Battery Area | Electrical | start | Live conductors; Damaged insulation | Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-10-27 10:45 | 2025-10-27 18:45 | 2025-10-27 21:45 | isolation_certificate_12.pdf | Closed | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-10-27 | 2025-10-27 18:45 | FALSE
PTW-5027 | Deepak Raut | Maintenance Fitter | Maintenance Workshop | Hot Work | start | Combustible dust presence; Sparks near solvent storage | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-09-03 07:15 | 2025-09-03 11:15 | 2025-09-03 11:15 | isolation_certificate_12.pdf | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-09-03 | 2025-09-03 11:15 | FALSE
PTW-5028 | Priya Joshi | Process Engineer | Assembly - Line 5 | Electrical | start | Water ingress risk; Damaged insulation | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | QA Head - Mr. Manoj Desai | QA Head | 2025-08-21 10:00 | 2025-08-21 18:00 | 2025-08-21 11:00 | hotwork_checklist_5.pdf | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-21 | 2025-08-21 18:00 | FALSE
PTW-5029 | Swapnil Gawade | Assembly Lead | Underground Tank Area | Excavation | stop | Nearby vehicle movement | Underground utility check; Shoring in place; Access ladder; Dewatering plan | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-08-05 06:00 | 2025-08-05 18:00 | 2025-08-05 19:00 | none | Closed | Yes | Underground utility check; Shoring in place; Access ladder |  | 2025-08-05 | 2025-08-05 18:00 | FALSE
PTW-5030 | Priya Joshi | Process Engineer | Testing - Dyno Bay | Confined Space | stop | Toxic gas presence (CO) | Gas test record; Entry permit signed; Rescue team standby; Ventilation provided | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-09-09 09:15 | 2025-09-09 21:15 | 2025-09-09 12:15 | scaffold_report_7.pdf | Closed | Yes | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-09 | 2025-09-09 21:15 | FALSE
PTW-5031 | Anita Bhosale | Quality Inspector | Stamping - Bay 1 | Working at Height | stop | Falling objects | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | QA Head - Mr. Manoj Desai | QA Head | 2025-10-04 16:30 | 2025-10-04 20:30 | 2025-10-04 22:30 | none | Closed | No | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-10-04 | 2025-10-04 20:30 | FALSE
PTW-5032 | Priya Joshi | Process Engineer | Body Shop - Booth A | Confined Space | start | Poor ventilation; Oxygen deficiency | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | HR Manager - Ms. Jyoti Rane | HR Manager | 2025-09-11 09:00 | 2025-09-12 09:00 | 2025-09-11 17:00 | none | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-11 | 2025-09-12 09:00 | FALSE
PTW-5033 | Asha Kulkarni | Maintenance Technician | Testing - Dyno Bay | Chemical Transfer | start | Corrosive splash; Vapour inhalation | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-08-01 07:30 | 2025-08-01 13:30 |  | none | Open | Yes | SDS reviewed; Spill kit available; Proper PPE |  | 2025-08-01 | 2025-08-01 13:30 | TRUE
PTW-5034 | Ajay Kadam | Contractor Foreman | Body Shop - Booth A | Chemical Transfer | stop | Corrosive splash | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-08-20 16:45 | 2025-08-21 16:45 | 2025-08-21 16:45 | none | Closed | No | SDS reviewed; Spill kit available; Proper PPE |  | 2025-08-20 | 2025-08-21 16:45 | FALSE
PTW-5035 | Shyamrao Jagtap | Rigger | Welding - Line 3 | Chemical Transfer | start | Vapour inhalation | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-08-18 14:00 | 2025-08-18 18:00 | 2025-08-18 22:00 | none | Closed | No | SDS reviewed; Spill kit available; Proper PPE |  | 2025-08-18 | 2025-08-18 18:00 | FALSE
PTW-5036 | Rutuja Kale | Chemical Operator | Maintenance Workshop | Excavation | stop | Nearby vehicle movement | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-08-07 16:00 | 2025-08-08 16:00 | 2025-08-07 19:00 | none | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-08-07 | 2025-08-08 16:00 | FALSE
PTW-5037 | Asha Kulkarni | Maintenance Technician | Paint - Oven Area | Chemical Transfer | start | Ignition source nearby | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | QA Head - Mr. Manoj Desai | QA Head | 2025-08-09 13:30 | 2025-08-10 01:30 |  | hotwork_checklist_5.pdf | Open | Yes | SDS reviewed; Spill kit available; Proper PPE |  | 2025-08-09 | 2025-08-10 01:30 | TRUE
PTW-5038 | Mohan Dighe | External Contractor | Battery Area | Hot Work | stop | Sparks near solvent storage; Fire ignition | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-08-06 15:15 | 2025-08-07 03:15 | 2025-08-06 19:15 | photo_area_22.jpg | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-08-06 | 2025-08-07 03:15 | FALSE
PTW-5039 | Swapnil Gawade | Assembly Lead | Maintenance Workshop | Excavation | stop | Collapse/soil instability; Water ingress | Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | QA Head - Mr. Manoj Desai | QA Head | 2025-10-27 13:30 | 2025-10-28 01:30 |  | sds_hydrochloric.pdf | Open | Yes | Underground utility check; Shoring in place; Access ladder |  | 2025-10-27 | 2025-10-28 01:30 | TRUE
PTW-5040 | Sanjay Mahajan | Fabrication Lead | Paint - Oven Area | Confined Space | start | Toxic gas presence (CO) | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-08-11 14:45 | 2025-08-11 22:45 | 2025-08-11 17:45 | none | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-08-11 | 2025-08-11 22:45 | FALSE
PTW-5041 | Kiran Jadhav | Paint Technician | Testing - Dyno Bay | Electrical | start | Live conductors | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-09-05 07:30 | 2025-09-05 19:30 | 2025-09-05 12:30 | scaffold_report_7.pdf | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-09-05 | 2025-09-05 19:30 | FALSE
PTW-5042 | Ajay Kadam | Contractor Foreman | Battery Area | Hot Work | stop | Fire ignition; Combustible dust presence | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | Plant Manager - Mr. Amit Mehta | Plant Manager | 2025-09-15 12:30 | 2025-09-15 20:30 | 2025-09-15 14:30 | scaffold_report_7.pdf | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-09-15 | 2025-09-15 20:30 | FALSE
PTW-5043 | Pooja Nimbalkar | Safety Coordinator | Stamping - Bay 1 | Confined Space | stop | Oxygen deficiency | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | QA Head - Mr. Manoj Desai | QA Head | 2025-09-19 15:00 | 2025-09-19 23:00 | 2025-09-19 18:00 | photo_area_22.jpg | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-19 | 2025-09-19 23:00 | FALSE
PTW-5044 | Nilesh Chavan | HVAC Technician | Stamping - Bay 1 | Electrical | stop | Live conductors | Isolation verified; Lockout-Tagout applied; Insulation checked; Voltage tester reading attached | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-09-04 12:30 | 2025-09-05 00:30 | 2025-09-04 17:30 | hotwork_checklist_5.pdf | Closed | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-09-04 | 2025-09-05 00:30 | FALSE
PTW-5045 | Kiran Jadhav | Paint Technician | Battery Area | Electrical | stop | Damaged insulation; Water ingress risk | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-10-02 06:15 | 2025-10-02 14:15 | 2025-10-02 10:15 | hotwork_checklist_5.pdf | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-10-02 | 2025-10-02 14:15 | FALSE
PTW-5046 | Rakesh More | Electrician | Welding - Line 3 | Hot Work | start | Sparks near solvent storage; Combustible dust presence | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-10-01 14:45 | 2025-10-02 02:45 | 2025-10-02 08:45 | photo_area_22.jpg | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-10-01 | 2025-10-02 02:45 | FALSE
PTW-5047 | Rutuja Kale | Chemical Operator | Battery Area | Confined Space | start | Engulfment risk; Poor ventilation | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-09-01 07:15 | 2025-09-01 11:15 | 2025-09-01 14:15 | scaffold_report_7.pdf | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-01 | 2025-09-01 11:15 | FALSE
PTW-5048 | Deepak Raut | Maintenance Fitter | Stamping - Bay 1 | LOTO | stop | Hydraulic pressure; Unexpected energization | Energy isolation verified; Lock and tag present; Authorized personnel only; LOTO checklist completed | HR Manager - Ms. Jyoti Rane | HR Manager | 2025-09-22 14:15 | 2025-09-23 14:15 | 2025-09-23 18:15 | photo_area_22.jpg | Closed | No | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-09-22 | 2025-09-23 14:15 | FALSE
PTW-5049 | Sanjay Mahajan | Fabrication Lead | Testing - Dyno Bay | LOTO | stop | Stored energy in springs | Energy isolation verified; Lock and tag present; Authorized personnel only | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-08-12 10:15 | 2025-08-13 10:15 | 2025-08-12 13:15 | scaffold_report_7.pdf | Closed | Yes | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-08-12 | 2025-08-13 10:15 | FALSE
PTW-5050 | Vikram Shinde | Welder | Body Shop - Booth A | Electrical | start | Water ingress risk | Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-07 13:45 | 2025-10-07 17:45 | 2025-10-07 17:45 | ptw_form_001.pdf | Closed | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-10-07 | 2025-10-07 17:45 | FALSE
PTW-5051 | Deepak Raut | Maintenance Fitter | Welding - Line 3 | Excavation | start | Water ingress | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-10-22 10:15 | 2025-10-23 10:15 | 2025-10-22 19:15 | photo_area_22.jpg | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-10-22 | 2025-10-23 10:15 | FALSE
PTW-5052 | Sunita Gaikwad | Operator | Assembly - Line 5 | Working at Height | stop | Wind gusts | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-10-16 06:00 | 2025-10-17 06:00 | 2025-10-16 20:00 | hotwork_checklist_5.pdf | Closed | No | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-10-16 | 2025-10-17 06:00 | FALSE
PTW-5053 | Pooja Nimbalkar | Safety Coordinator | Assembly - Line 5 | LOTO | start | Hydraulic pressure; Unexpected energization | Energy isolation verified; Lock and tag present; Authorized personnel only; LOTO checklist completed | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-08-08 06:15 | 2025-08-08 14:15 | 2025-08-08 12:15 | scaffold_report_7.pdf | Closed | No | Energy isolation verified; Lock and tag present; Authorized personnel only |  | 2025-08-08 | 2025-08-08 14:15 | FALSE
PTW-5054 | Swapnil Gawade | Assembly Lead | Paint - Oven Area | Excavation | stop | Water ingress | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-08-26 06:30 | 2025-08-26 12:30 | 2025-08-26 10:30 | hotwork_checklist_5.pdf | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-08-26 | 2025-08-26 12:30 | FALSE
PTW-5055 | Rakesh More | Electrician | Maintenance Workshop | Working at Height | stop | Falling objects | Harness and lanyard; Scaffold inspection record; Edge protection; Tool tethering; Weather check | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-09-08 07:45 | 2025-09-08 11:45 | 2025-09-08 17:45 | gas_test_45.pdf | Closed | No | Harness and lanyard; Scaffold inspection record; Edge protection |  | 2025-09-08 | 2025-09-08 11:45 | FALSE
PTW-5056 | Sanjay Mahajan | Fabrication Lead | Battery Area | Electrical | start | Arc flash potential | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-09-23 06:00 | 2025-09-23 12:00 | 2025-09-23 15:00 | sds_hydrochloric.pdf | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-09-23 | 2025-09-23 12:00 | FALSE
PTW-5057 | Nilesh Chavan | HVAC Technician | Maintenance Workshop | Chemical Transfer | start | Corrosive splash | Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | HR Manager - Ms. Jyoti Rane | HR Manager | 2025-08-05 10:45 | 2025-08-05 18:45 | 2025-08-05 12:45 | none | Closed | Yes | SDS reviewed; Spill kit available; Proper PPE |  | 2025-08-05 | 2025-08-05 18:45 | FALSE
PTW-5058 | Sunita Gaikwad | Operator | Welding - Line 3 | Chemical Transfer | start | Vapour inhalation; Ignition source nearby | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-08-27 12:30 | 2025-08-28 00:30 | 2025-08-28 00:30 | sds_hydrochloric.pdf | Closed | No | SDS reviewed; Spill kit available; Proper PPE |  | 2025-08-27 | 2025-08-28 00:30 | FALSE
PTW-5059 | Sanjay Mahajan | Fabrication Lead | Testing - Dyno Bay | Electrical | start | Live conductors; Water ingress risk | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Plant Manager - Mr. Amit Mehta | Plant Manager | 2025-08-04 16:45 | 2025-08-04 20:45 | 2025-08-04 22:45 | lockout_tags.xlsx | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-04 | 2025-08-04 20:45 | FALSE
PTW-5060 | Ajay Kadam | Contractor Foreman | Assembly - Line 5 | Confined Space | start | Oxygen deficiency | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | QA Head - Mr. Manoj Desai | QA Head | 2025-09-04 11:00 | 2025-09-04 15:00 | 2025-09-04 19:00 | scaffold_report_7.pdf | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-04 | 2025-09-04 15:00 | FALSE
PTW-5061 | Kiran Jadhav | Paint Technician | Stamping - Bay 1 | Electrical | stop | Arc flash potential | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-09-02 12:45 | 2025-09-02 20:45 | 2025-09-03 01:45 | isolation_certificate_12.pdf | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-09-02 | 2025-09-02 20:45 | FALSE
PTW-5062 | Rakesh More | Electrician | Testing - Dyno Bay | Chemical Transfer | start | Ignition source nearby | SDS reviewed; Spill kit available; Proper PPE; Bonding & grounding; Secondary containment | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-06 09:45 | 2025-10-06 17:45 | 2025-10-06 16:45 | isolation_certificate_12.pdf | Closed | No | SDS reviewed; Spill kit available; Proper PPE |  | 2025-10-06 | 2025-10-06 17:45 | FALSE
PTW-5063 | Vikram Shinde | Welder | Maintenance Workshop | Electrical | stop | Arc flash potential | Isolation verified; Lockout-Tagout applied; Insulation checked; Voltage tester reading attached | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-08-11 10:00 | 2025-08-12 10:00 | 2025-08-11 18:00 | none | Closed | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-11 | 2025-08-12 10:00 | FALSE
PTW-5064 | Deepak Raut | Maintenance Fitter | Battery Area | Confined Space | stop | Toxic gas presence (CO); Poor ventilation | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | QA Head - Mr. Manoj Desai | QA Head | 2025-10-25 07:30 | 2025-10-25 13:30 | 2025-10-25 12:30 | photo_area_22.jpg | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-10-25 | 2025-10-25 13:30 | FALSE
PTW-5065 | Anita Bhosale | Quality Inspector | Welding - Line 3 | Confined Space | stop | Oxygen deficiency | Gas test record; Atmospheric monitor present; Rescue team standby; Ventilation provided | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-09-11 07:45 | 2025-09-11 19:45 | 2025-09-11 09:45 | hotwork_checklist_5.pdf | Closed | Yes | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-11 | 2025-09-11 19:45 | FALSE
PTW-5066 | Mohan Dighe | External Contractor | Welding - Line 3 | Electrical | stop | Water ingress risk | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-08-30 07:00 | 2025-08-30 11:00 |  | lockout_tags.xlsx | Open | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-08-30 | 2025-08-30 11:00 | TRUE
PTW-5067 | Meena Pawar | Line Operator | Paint - Oven Area | Confined Space | stop | Toxic gas presence (CO) | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby; Ventilation provided | Plant Manager - Mr. Amit Mehta | Plant Manager | 2025-08-28 06:30 | 2025-08-28 14:30 | 2025-08-28 12:30 | gas_test_45.pdf | Closed | No | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-08-28 | 2025-08-28 14:30 | FALSE
PTW-5068 | Rahul Deshmukh | Shift Supervisor | Underground Tank Area | Electrical | stop | Water ingress risk | Isolation verified; Lockout-Tagout applied; Insulation checked; Voltage tester reading attached | Site Engineer - Mr. Vikrant Deshpande | Site Engineer | 2025-10-20 10:00 | 2025-10-21 10:00 | 2025-10-21 04:00 | isolation_certificate_12.pdf | Closed | Yes | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-10-20 | 2025-10-21 10:00 | FALSE
PTW-5069 | Deepak Raut | Maintenance Fitter | Assembly - Line 5 | Excavation | stop | Collapse/soil instability; Underground cable strike | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Shift Incharge - Mr. Prakash Yadav | Shift Incharge | 2025-10-23 08:45 | 2025-10-23 16:45 | 2025-10-23 09:45 | lockout_tags.xlsx | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-10-23 | 2025-10-23 16:45 | FALSE
PTW-5070 | Sanjay Mahajan | Fabrication Lead | Stamping - Bay 1 | Excavation | stop | Nearby vehicle movement | Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-22 09:45 | 2025-10-22 21:45 | 2025-10-22 21:45 | sds_hydrochloric.pdf | Closed | Yes | Underground utility check; Shoring in place; Access ladder |  | 2025-10-22 | 2025-10-22 21:45 | FALSE
PTW-5071 | Rutuja Kale | Chemical Operator | Testing - Dyno Bay | Hot Work | start | Sparks near solvent storage; Fire ignition | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site; Welding blanket; Gas-free certificate if needed | HOD Production - Ms. Neeta Kulkarni | HOD Production | 2025-08-21 08:00 | 2025-08-21 14:00 | 2025-08-21 10:00 | isolation_certificate_12.pdf | Closed | No | Fire watch assigned; Hot work permit displayed; Fire extinguisher at site |  | 2025-08-21 | 2025-08-21 14:00 | FALSE
PTW-5072 | Meena Pawar | Line Operator | Maintenance Workshop | Confined Space | stop | Poor ventilation | Gas test record; Entry permit signed; Atmospheric monitor present; Rescue team standby | Plant Manager - Mr. Amit Mehta | Plant Manager | 2025-09-19 13:15 | 2025-09-19 19:15 | 2025-09-19 17:15 | scaffold_report_7.pdf | Closed | Yes | Gas test record; Entry permit signed; Atmospheric monitor present |  | 2025-09-19 | 2025-09-19 19:15 | FALSE
PTW-5073 | Shyamrao Jagtap | Rigger | Stamping - Bay 1 | Electrical | stop | Water ingress risk | Isolation verified; Lockout-Tagout applied; Insulation checked; Qualified electrician present; Voltage tester reading attached | Maintenance Head - Mr. Ramesh Patil | Maintenance Head | 2025-10-18 09:45 | 2025-10-18 15:45 | 2025-10-18 21:45 | photo_area_22.jpg | Closed | No | Isolation verified; Lockout-Tagout applied; Insulation checked |  | 2025-10-18 | 2025-10-18 15:45 | FALSE
PTW-5074 | Ajay Kadam | Contractor Foreman | Testing - Dyno Bay | Excavation | stop | Nearby vehicle movement; Underground cable strike | Underground utility check; Shoring in place; Access ladder; Spoil pile positioned; Dewatering plan | Safety Officer - Mr. Sagar Dani | Safety Officer | 2025-08-06 14:00 | 2025-08-07 02:00 | 2025-08-07 02:00 | sds_hydrochloric.pdf | Closed | No | Underground utility check; Shoring in place; Access ladder |  | 2025-08-06 | 2025-08-07 02:00 | FALSE

## PTW_KPIs_By_Area
area | open_permits | permits_past_expiry | missing_controls | total_permits
Assembly - Line 5 | 0 | 0 | 0 | 6
Battery Area | 0 | 0 | 2 | 10
Body Shop - Booth A | 1 | 1 | 3 | 9
Maintenance Workshop | 1 | 1 | 5 | 11
Paint - Oven Area | 1 | 1 | 2 | 7
Stamping - Bay 1 | 0 | 0 | 2 | 9
Testing - Dyno Bay | 2 | 2 | 4 | 10
Underground Tank Area | 1 | 1 | 3 | 6
Welding - Line 3 | 1 | 1 | 2 | 7